**03/01/2017**

* We further clarified that this project is about globalization and specifically about migration.  All aspects of migration should be explored and identified, from "why" to "where", "how" and "what"?  The entire migration cycle - Why do people migrate? - How do they migrate? What happens when they migrate? What are some of the challenges and success stories?
* We will first identify the data sources as much as we can and then determine which ones we would use for this project.
* The students will conduct this research in the next 2 weeks until our next meeting on March 22nd.
* The data sources and any other information we gather should be deposited in this google drive :
  + <https://drive.google.com/drive/folders/0Bzp7a8gYG43_OFhwZGhDckNvWWc>
* Brian suggested that when the students develop code it is encouraged that they deposit the code in a GitHub folder.
* The suggested timeline for this project is as follows:
  + Data identification and gathering - March 22
  + Data analysis and visualization - April 30
  + Automation of data viz and integration with the installation servers - May 31
  + Testing and modification - June 30 (this phase does not require much student involvement except for potential fixes and modification\_
  + First public exhibit - July 8th at Hirshhorn Museum in DC
* Bardia mentioned that a parallel effort will be underway to collect real time stories from people which will be played back in the installation.